## Planilha1
Story | Task | Estimate min (hr) | Estimate max (hr) | Actual | Comment
Setup | Setup microservices | 1.5 | 2.5 | 2.5 | Created folder structure and separated services into FastAPI apps
Data | Load & index product data | 1.5 | 2.0 | 1.5 | Loaded product CSV, parsed and prepared fields for indexing
Product Service | Implement product search service | 1.5 | 2.5 | 2 | Built search logic and endpoint with test responses
Order Service | Implement order lookup service | 1.5 | 2.5 | 2.5 | Replaced mock API with real CSV parsing logic
Chat Service | Implement chat router service | 1.5 | 2.5 | 2 | Handled routing and keyword-based decision logic
RAG (v1) | Initial RAG integration (TF-IDF) | 2.5 | 3.5 | 3.5 | Used TF-IDF and cosine similarity for retrieval
Q&A | Test and validate sample queries | 1.5 | 2.5 | 2 | Generated and tested sample input/output scenarios
Infra | Run and test locally | 1.0 | 2.0 | 1.5 | Ran all services in parallel and tested integration via curl/Postman
Docs | Write README and usage guide | 1.0 | 1.5 | 1.5 | Updated instructions, sample interactions, architecture notes
RAG (v2) | Upgrade to semantic RAG with FAISS | 2.5 | 3.5 | 4 | Added sentence-transformers, FAISS and fixed dataset columns